IMPLEMENTATION PRD

Founder Copilot

Full-Stack Build Specification — Solo Developer

| Field | Detail |
| --- | --- |
| Stack | Next.js 14 · Tailwind · Supabase · Claude API · Whisper · Stripe |
| Builder | Solo |
| Version | 1.0 — MVP |
| Timeline | 12–14 weeks |
| Doc type | Implementation spec — schema, API routes, components, sprint tasks |
| Date | March 31, 2026 |

# 1. Architecture Overview

Single Next.js 14 app using the App Router. Supabase handles auth, database, and storage. All LLM calls go server-side via Next.js API routes — no client-side API key exposure. Stripe handles billing via webhooks.

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | Next.js 14 (App Router) + Tailwind CSS | UI, routing, server components |
| Auth | Supabase Auth (email + magic link) | Session management, RLS enforcement |
| Database | Supabase Postgres + Row Level Security | All app data, isolated per user |
| File Storage | Supabase Storage | Audio/video uploads, transcript files |
| Transcription | OpenAI Whisper API (via server route) | Audio/video → transcript text |
| AI Generation | Anthropic Claude API (claude-sonnet-4-20250514) | All content generation + extraction |
| Billing | Stripe Checkout + Webhooks | Subscriptions, plan enforcement |
| Deployment | Vercel (frontend + API routes) | Zero-ops hosting for solo build |

## Request flow — content generation

Client (browser)

→ POST /api/generate  (Next.js API route, server-side)

→ Fetch founder profile + voice model from Supabase

→ Build system prompt with profile context

→ Call Claude API (claude-sonnet-4-20250514)

→ Stream response back to client

→ Save outputs to Supabase on completion

← Streamed output rendered in UI

## Request flow — file transcription

Client uploads file

→ POST /api/transcribe

→ Upload to Supabase Storage

→ Send to OpenAI Whisper API

→ Store transcript text in inputs table

→ Trigger extraction pipeline

← Return transcript + extracted insights

# 2. Database Schema

RLS rule  Every table has user_id with a Supabase RLS policy: auth.uid() = user_id. No cross-user data access possible.

## 2.1 users (extends Supabase auth.users)

Table: profiles

id              uuid  PRIMARY KEY  references auth.users(id)

created_at      timestamptz  DEFAULT now()

updated_at      timestamptz

full_name       text

plan            text  DEFAULT 'free'   -- free | starter | pro

inputs_used     int   DEFAULT 0

inputs_limit    int   DEFAULT 3        -- free tier limit

stripe_customer_id  text

stripe_subscription_id  text

## 2.2 founder_profiles

Table: founder_profiles

id              uuid  PRIMARY KEY  DEFAULT gen_random_uuid()

user_id         uuid  REFERENCES profiles(id)  NOT NULL

created_at      timestamptz  DEFAULT now()

updated_at      timestamptz

-- Identity

product_name    text

stage           text   -- pre_revenue | sub_10k | 10_50k | 50k_plus

gtm_focus       text   -- awareness | validation | conversion | retention

primary_channel text   -- linkedin | reddit | x | email | all

-- ICP

icp_role        text   -- e.g. 'Founder, Head of Growth'

icp_industry    text

icp_company_size text  -- e.g. '1-10 employees'

core_problem    text   -- 1-2 sentence problem statement

pain_1          text

pain_2          text

pain_3          text

-- Voice model

voice_samples   text[]  -- array of raw sample posts

voice_summary   text    -- plain-English voice description (AI-extracted)

voice_prompt    text    -- injected into generation system prompt

-- Brand voice (company page)

brand_samples   text[]

brand_summary   text

brand_prompt    text

## 2.3 inputs

Table: inputs

id              uuid  PRIMARY KEY  DEFAULT gen_random_uuid()

user_id         uuid  REFERENCES profiles(id)  NOT NULL

created_at      timestamptz  DEFAULT now()

title           text

source_type     text   -- url | file_upload | text_paste

source_url      text   -- Loom/YouTube URL if applicable

storage_path    text   -- Supabase Storage path for uploaded file

duration_secs   int

status          text   -- processing | ready | failed

-- Content

raw_transcript  text

insights        jsonb  -- { pains:[], outcomes:[], objections:[], stories:[] }

insights_edited jsonb  -- user-edited version of insights

## 2.4 outputs

Table: outputs

id              uuid  PRIMARY KEY  DEFAULT gen_random_uuid()

user_id         uuid  REFERENCES profiles(id)  NOT NULL

input_id        uuid  REFERENCES inputs(id)  NOT NULL

created_at      timestamptz  DEFAULT now()

updated_at      timestamptz

channel         text   -- linkedin_founder | linkedin_company | reddit

-- x | email | landing

angle           text   -- problem | story | objection | benefit

variant_index   int    -- 0,1,2... (multiple variants per channel)

routing_tag     text   -- founder_first | company_first | both

content         text   -- the generated post/copy

content_edited  text   -- user-edited version

-- Experiment tracking

experiment_name text

status          text   DEFAULT 'to_try'  -- to_try | worked | didnt_work

manual_clicks   int

manual_replies  int

manual_signups  int

notes           text

## 2.5 distribution_suggestions

Table: distribution_suggestions

id              uuid  PRIMARY KEY  DEFAULT gen_random_uuid()

input_id        uuid  REFERENCES inputs(id)  NOT NULL

user_id         uuid  REFERENCES profiles(id)  NOT NULL

created_at      timestamptz  DEFAULT now()

type            text   -- subreddit | linkedin_hook | hashtag | community

value           text   -- e.g. 'r/SaaS', '#founderlife'

rationale       text   -- why suggested

priority        int    -- 1=highest

# 3. API Routes

Convention  All routes live in /app/api/. All require a valid Supabase session (checked via createRouteHandlerClient). Return JSON. Errors return { error: string } with appropriate HTTP status.

## 3.1 Ingestion

| Route | Method | Purpose | Key logic |
| --- | --- | --- | --- |
| /api/ingest/url | POST | Ingest Loom/YouTube URL | Fetch transcript via yt-dlp or Loom API → save to inputs table → trigger extraction |
| /api/ingest/upload | POST | Upload audio/video/txt file | Receive multipart form → upload to Supabase Storage → send to Whisper → save transcript → trigger extraction |
| /api/ingest/paste | POST | Save raw pasted transcript | Validate text → save to inputs → trigger extraction immediately |
| /api/ingest/[id]/status | GET | Poll processing status | Return inputs.status for given id — client polls every 3s while processing |

## 3.2 Extraction

| Route | Method | Purpose | Key logic |
| --- | --- | --- | --- |
| /api/extract/[inputId] | POST | Extract insights from transcript | Build Claude prompt with transcript → stream extraction → parse JSON clusters → save to inputs.insights |
| /api/extract/[inputId]/edit | PATCH | Save user-edited insights | Validate + save to inputs.insights_edited → use edited version for generation |

## 3.3 Generation

| Route | Method | Purpose | Key logic |
| --- | --- | --- | --- |
| /api/generate | POST | Generate multi-channel outputs | Fetch founder_profile + voice_prompt + insights → build system prompt → call Claude (streaming) → save each output to outputs table |
| /api/generate/[outputId] | PATCH | Save edited output | Save content_edited to outputs table |
| /api/generate/[outputId]/regenerate | POST | Regenerate single output | Re-call Claude for that channel+angle only → update outputs row |
| /api/generate/voice-model | POST | Extract voice model from samples | Send 3-5 sample posts to Claude → extract voice_summary + voice_prompt → save to founder_profiles |

## 3.4 Distribution

| Route | Method | Purpose | Key logic |
| --- | --- | --- | --- |
| /api/distribute/[inputId] | POST | Generate distribution suggestions | Extract keywords from insights + founder_profile ICP → Claude suggests subreddits, hooks, hashtags → save to distribution_suggestions |

## 3.5 Founder Profile

| Route | Method | Purpose | Key logic |
| --- | --- | --- | --- |
| /api/profile | GET | Fetch founder profile | Return founder_profiles row for auth user |
| /api/profile | POST | Create founder profile | Validate + insert founder_profiles row |
| /api/profile | PATCH | Update founder profile | Partial update — validate fields → update row → regenerate voice_prompt if samples changed |

## 3.6 Experiments

| Route | Method | Purpose | Key logic |
| --- | --- | --- | --- |
| /api/experiments | GET | List all experiments | Return outputs with experiment fields populated, ordered by created_at |
| /api/experiments/[outputId] | PATCH | Update experiment status/metrics | Update status, manual_clicks, manual_replies, manual_signups, notes |
| /api/experiments/summary | GET | Monthly summary | Aggregate worked vs didnt_work by channel + angle → return top performing combination |

## 3.7 Billing

| Route | Method | Purpose | Key logic |
| --- | --- | --- | --- |
| /api/billing/checkout | POST | Create Stripe Checkout session | Create Stripe customer if needed → create checkout session → return URL |
| /api/billing/portal | POST | Open Stripe billing portal | Return Stripe portal URL for subscription management |
| /api/billing/webhook | POST | Handle Stripe webhooks | Handle: checkout.completed → upgrade plan; subscription.deleted → downgrade; payment_failed → notify |

# 4. Claude Prompt Architecture

All Claude calls are made server-side. The system prompt is assembled dynamically from the founder's profile. Never hardcode prompts — build them from profile data so every user gets personalised output.

## 4.1 Insight extraction prompt

SYSTEM:

You are an insight extraction engine for a B2B SaaS GTM tool.

Extract structured insights from founder call transcripts.

Return ONLY valid JSON. No preamble. No markdown.

JSON schema:

{

pains: [{ text: string, quote: string }],

outcomes: [{ text: string, quote: string }],

objections: [{ text: string, quote: string }],

stories: [{ text: string, quote: string }]

}

USER:

Extract insights from this transcript.

ICP context: {icp_role} at {icp_industry} companies.

Core problem the product solves: {core_problem}

Transcript:

{transcript}

## 4.2 Voice model extraction prompt

SYSTEM:

You are a writing style analyst.

Analyse the sample posts and return ONLY valid JSON.

JSON schema:

{

summary: string,  // plain English, 2-3 sentences

prompt: string    // system prompt fragment to inject into generation

}

The prompt field should describe:

- Sentence length and rhythm

- Vocabulary level (technical / plain / casual)

- Use of lists vs prose

- Directness level

- Emoji usage

- CTA style

- Things to always avoid

USER:

Analyse these sample posts and extract a voice profile.

Sample posts:

{samples joined by ---}

## 4.3 Content generation prompt

SYSTEM:

You are a GTM content engine for early-stage SaaS founders.

Generate channel-ready content from founder insights.

Founder context:

- Product: {product_name}

- Stage: {stage}

- ICP: {icp_role} at {icp_industry}, {icp_company_size}

- Core problem: {core_problem}

- Top pains: {pain_1}, {pain_2}, {pain_3}

- GTM focus: {gtm_focus}

Voice profile:

{voice_prompt}

Generation rules:

- Never sound like generic AI

- Match the voice profile exactly

- Every post must be grounded in the insights provided

- Founder variant: first-person, human, opinionated

- Company variant: third-person, polished, product-aware

- Return ONLY valid JSON. No preamble.

JSON schema:

{

linkedin_founder: [{ angle: string, content: string }],  // 3 variants

linkedin_company: [{ angle: string, content: string }],  // 3 variants

reddit: [{ angle: string, title: string, content: string }],  // 2

x: [{ angle: string, content: string }],  // 2

email: { subject: string, content: string },

landing: { headline: string, subhead: string, bullets: string[] }

}

USER:

Generate content from these insights:

{insights_edited or insights as JSON}

## 4.4 Distribution suggestions prompt

SYSTEM:

You are a B2B SaaS distribution advisor.

Suggest where and how to distribute this content.

Return ONLY valid JSON.

JSON schema:

{

subreddits: [{ name: string, rationale: string, angle: string }],

linkedin_hooks: [{ hook: string, rationale: string }],

hashtags: string[],

routing: {

recommendation: 'founder_first'|'company_first'|'both',

rationale: string

}

}

USER:

Suggest distribution for content based on:

- ICP: {icp_role}, {icp_industry}

- Stage: {stage}

- GTM focus: {gtm_focus}

- Key themes from insights: {top 5 pain/insight keywords}

# 5. Component Architecture

Convention  All components in /components. Pages in /app. Shared UI primitives (Button, Card, Badge, Input) in /components/ui. Data-fetching in Server Components where possible; interactive elements as Client Components.

## 5.1 Page structure

| Route | Page | Notes |
| --- | --- | --- |
| / | Landing page | Marketing page, pricing, CTA to sign up |
| /auth/login | Login page | Supabase magic link + email/password |
| /onboarding | Onboarding wizard | Founder Profile setup + voice model — required before first input |
| /dashboard | Dashboard | Recent inputs, quick stats, new input CTA |
| /input/new | New input page | URL / upload / paste tabs |
| /input/[id] | Input detail page | Transcript, insights editor, generate button |
| /input/[id]/outputs | Outputs page | All generated outputs, dual-channel view, copy/export |
| /experiments | Experiments board | All outputs with status, filters, monthly summary |
| /profile | Founder profile page | Edit profile, voice model, brand voice |
| /settings | Settings | Billing, plan, account |

## 5.2 Core components

| Component | Location | Purpose |
| --- | --- | --- |
| OnboardingWizard | components/onboarding/ | Multi-step founder profile + voice setup. Steps: identity, ICP, voice samples, confirmation |
| InputTabs | components/input/InputTabs.tsx | URL / Upload / Paste tab switcher. Each tab is a separate component |
| TranscriptView | components/input/TranscriptView.tsx | Read-only transcript display with word count and copy button |
| InsightChips | components/input/InsightChips.tsx | Editable chips for pains/outcomes/objections/stories. Add/remove/edit per chip |
| GenerateButton | components/input/GenerateButton.tsx | Triggers /api/generate. Shows loading state. Disabled if insights empty |
| OutputCard | components/outputs/OutputCard.tsx | Single output card: content, channel badge, angle badge, edit/copy/regen buttons |
| DualChannelView | components/outputs/DualChannelView.tsx | Side-by-side founder + company LinkedIn variants with routing tag selector |
| RoutingTag | components/outputs/RoutingTag.tsx | Founder-first / Company-first / Both selector. Auto-set, user-editable |
| ExperimentBoard | components/experiments/ExperimentBoard.tsx | Kanban-style or list view: To Try / Worked / Didn't Work columns |
| ExperimentCard | components/experiments/ExperimentCard.tsx | Output card with status toggle + manual metrics input |
| VoiceModelSetup | components/profile/VoiceModelSetup.tsx | Textarea for samples, extract button, plain-English summary display |
| DistributionSuggestions | components/distribution/Suggestions.tsx | Subreddit cards, hook suggestions, hashtag badges, copy buttons |
| PlanGate | components/billing/PlanGate.tsx | Wrapper that blocks action + shows upgrade modal if user is over limit |
| UsageBar | components/billing/UsageBar.tsx | Shows inputs_used / inputs_limit progress bar in dashboard |
| StreamingText | components/ui/StreamingText.tsx | Renders Claude streaming response token by token |

# 6. Auth & Plan Enforcement

## 6.1 Auth flow

- User signs up with email → Supabase sends magic link

- On confirm → Supabase creates auth.users row → trigger creates profiles row with plan='free', inputs_limit=3

- User redirected to /onboarding → must complete before accessing /dashboard

- Session stored in Supabase cookie — all API routes validate via createRouteHandlerClient

## 6.2 Plan limits

| Plan | Monthly inputs | Price | Stripe price_id |
| --- | --- | --- | --- |
| Free | 3 inputs | $0 | — (no Stripe) |
| Starter | 20 inputs | $29/mo | price_starter_monthly |
| Pro | Unlimited | $79/mo | price_pro_monthly |

Enforcement pattern  Before every /api/ingest/* call: fetch profiles.inputs_used and inputs_limit. If used >= limit, return 403 with { error: 'limit_reached', plan: current_plan }. Client shows PlanGate modal.

## 6.3 Stripe webhook handler

POST /api/billing/webhook

checkout.session.completed:

→ update profiles.plan based on price_id

→ update profiles.inputs_limit (20 or unlimited)

→ save stripe_subscription_id

customer.subscription.deleted:

→ downgrade profiles.plan to 'free'

→ set inputs_limit back to 3

invoice.payment_failed:

→ send email warning (via Supabase Edge Function or Resend)

# 7. Streaming Implementation

Claude generation is streamed to give instant feedback. Use the Vercel AI SDK or manual ReadableStream — do not wait for the full response before rendering.

## Server-side — /api/generate

import Anthropic from '@anthropic-ai/sdk';

export async function POST(req: Request) {

// ... auth check, fetch profile, build prompt ...

const stream = await anthropic.messages.stream({

model: 'claude-sonnet-4-20250514',

max_tokens: 4096,

system: systemPrompt,

messages: [{ role: 'user', content: userPrompt }],

});

const encoder = new TextEncoder();

const readable = new ReadableStream({

async start(controller) {

for await (const chunk of stream) {

if (chunk.type === 'content_block_delta') {

controller.enqueue(encoder.encode(chunk.delta.text));

}

}

// Save completed output to Supabase after stream ends

const full = await stream.finalMessage();

await saveOutputs(userId, inputId, full.content[0].text);

controller.close();

}

});

return new Response(readable, {

headers: { 'Content-Type': 'text/plain; charset=utf-8' }

});

}

## Client-side — StreamingText component

async function generate(inputId: string) {

const res = await fetch('/api/generate', {

method: 'POST',

body: JSON.stringify({ inputId }),

});

const reader = res.body!.getReader();

const decoder = new TextDecoder();

let buffer = '';

while (true) {

const { done, value } = await reader.read();

if (done) break;

buffer += decoder.decode(value, { stream: true });

setStreamingContent(buffer);  // update React state

}

// Parse final JSON from buffer, update outputs state

const outputs = JSON.parse(buffer);

setOutputs(outputs);

}

# 8. Project Folder Structure

/founder-copilot

/app

/api

/ingest         (url, upload, paste, [id]/status)

/extract        ([inputId], [inputId]/edit)

/generate       (index, [outputId], [outputId]/regenerate, voice-model)

/distribute     ([inputId])

/profile        (index GET/POST/PATCH)

/experiments    (index, [outputId], summary)

/billing        (checkout, portal, webhook)

/auth             (login, callback)

/onboarding       (page.tsx)

/dashboard        (page.tsx)

/input

/new            (page.tsx)

/[id]           (page.tsx — transcript + insights)

/[id]/outputs   (page.tsx — all outputs)

/experiments      (page.tsx)

/profile          (page.tsx)

/settings         (page.tsx)

layout.tsx

page.tsx          (landing)

/components

/ui               (Button, Card, Badge, Input, Modal, etc.)

/onboarding       (OnboardingWizard, steps/)

/input            (InputTabs, TranscriptView, InsightChips, GenerateButton)

/outputs          (OutputCard, DualChannelView, RoutingTag, ChannelBadge)

/experiments      (ExperimentBoard, ExperimentCard, MetricsInput)

/profile          (VoiceModelSetup, BrandVoiceSetup, ProfileForm)

/distribution     (Suggestions, SubredditCard, HookCard)

/billing          (PlanGate, UsageBar, PricingTable)

/lib

/supabase         (client.ts, server.ts, middleware.ts)

/claude           (client.ts, prompts.ts, buildSystemPrompt.ts)

/whisper          (transcribe.ts)

/stripe           (client.ts, plans.ts)

/utils            (cn.ts, format.ts, parse.ts)

/types

database.ts       (generated from Supabase)

app.ts            (Input, Output, FounderProfile, Experiment, etc.)

/supabase

/migrations       (one file per schema change)

seed.sql

middleware.ts       (Supabase session refresh)

.env.local          (SUPABASE_URL, SUPABASE_ANON_KEY, ANTHROPIC_API_KEY,

OPENAI_API_KEY, STRIPE_SECRET_KEY, STRIPE_WEBHOOK_SECRET)

# 9. Sprint Plan — 14 Weeks

Solo build rule  Each sprint is ~5 focused days. Ship something usable at the end of every sprint — no dead-end sprints. Test the core happy path after each sprint before moving on.

## Sprint 1 — Foundation (Week 1)

| Task | Detail | Done when |
| --- | --- | --- |
| Supabase project setup | Create project, enable auth, set up RLS | Can sign up + log in |
| DB migrations | Run migrations for all 5 tables | Tables exist with correct schema |
| Next.js scaffolding | App router, Tailwind, folder structure, env vars | App runs locally without errors |
| Auth flow | Login page, magic link, session, onboarding redirect | New user lands on /onboarding after signup |
| Supabase type gen | Generate TypeScript types from schema | types/database.ts exists and is accurate |

## Sprint 2 — Founder Profile + Voice Model (Week 2)

| Task | Detail | Done when |
| --- | --- | --- |
| OnboardingWizard | 4-step wizard: identity, ICP, pains, voice samples | User completes wizard, data saved to founder_profiles |
| /api/profile routes | GET, POST, PATCH with auth + validation | Profile can be created and updated via API |
| Voice model extraction | POST /api/generate/voice-model → Claude → save voice_prompt | voice_summary displays in plain English after samples submitted |
| Profile page | Edit existing profile, re-run voice extraction | Changes save and persist |

## Sprint 3 — Content Ingestion (Week 3)

| Task | Detail | Done when |
| --- | --- | --- |
| Text paste ingestion | POST /api/ingest/paste → save transcript → trigger extract | Pasted transcript saves and shows in input detail page |
| File upload ingestion | Upload to Supabase Storage → Whisper → save transcript | mp3/mp4/txt uploads transcribe correctly |
| URL ingestion | Loom/YouTube URL → transcript fetch → save | Loom URL produces transcript (use yt-dlp or Loom API) |
| Input list + detail page | Dashboard input list, /input/[id] transcript view | User can see all inputs and view transcript |
| Plan limit enforcement | Check inputs_used vs inputs_limit before ingest | Over-limit users see PlanGate modal, not error |

## Sprint 4 — Insight Extraction (Week 4)

| Task | Detail | Done when |
| --- | --- | --- |
| Extraction API | POST /api/extract/[inputId] → Claude → save JSON insights | Insights appear as chips after processing |
| InsightChips component | Editable chips per cluster (pains/outcomes/objections/stories) | User can add, edit, remove chips |
| Save edited insights | PATCH /api/extract/[inputId]/edit | Edits persist and are used in generation |
| Processing status polling | Client polls /api/ingest/[id]/status every 3s | Spinner shows while processing, chips appear when ready |

## Sprint 5 — Content Generation (Week 5–6)

| Task | Detail | Done when |
| --- | --- | --- |
| buildSystemPrompt utility | Assembles system prompt from founder_profile | Returns correct personalised prompt string |
| POST /api/generate | Fetch profile, build prompt, stream Claude response, save outputs | Outputs table populated after generation |
| Streaming UI | StreamingText component, loading states | User sees content streaming in real time |
| OutputCard component | Content display, channel badge, angle badge, copy button | Can copy any output to clipboard |
| Regenerate single output | POST /api/generate/[outputId]/regenerate | Single card regenerates without affecting others |
| Edit output | PATCH /api/generate/[outputId], content_edited persists | Edits save and show on refresh |

## Sprint 6 — Dual-Channel LinkedIn (Week 7)

| Task | Detail | Done when |
| --- | --- | --- |
| DualChannelView component | Side-by-side founder + company variants | Both variants visible on /input/[id]/outputs |
| RoutingTag component | Auto-assigned tag, user-editable dropdown | Tag saves to outputs.routing_tag |
| Routing auto-logic | Infer routing_tag from angle + content type | Tag is correct ≥70% of time without user editing |
| Brand voice setup | Optional brand voice samples + extraction on /profile | Brand voice prompt saved and used for company variants |

## Sprint 7 — Distribution Intelligence (Week 8)

| Task | Detail | Done when |
| --- | --- | --- |
| POST /api/distribute/[inputId] | Claude suggests subreddits, hooks, hashtags based on profile + insights | Suggestions saved to distribution_suggestions |
| Suggestions UI | SubredditCard, HookCard, hashtag badges, copy buttons | User can copy any suggestion to clipboard |
| Routing recommendation | Claude recommends founder-first / company-first / both | Shows as callout on outputs page |

## Sprint 8 — Experiments & Learning Loop (Week 9)

| Task | Detail | Done when |
| --- | --- | --- |
| Experiment tagging | Name + angle type + channel tag per output | Tags save to outputs table |
| ExperimentBoard | Kanban view: To Try / Worked / Didn't Work | User can drag or toggle status |
| Manual metrics | clicks/replies/signups input per output | Metrics save to outputs table |
| Monthly summary API | GET /api/experiments/summary → top performing angle+channel | Summary card shows on /experiments page |
| Learning loop | Worked outputs fed back as additional voice examples in future generation | System prompt includes top 3 worked outputs as style anchors |

## Sprint 9 — Billing (Week 10)

| Task | Detail | Done when |
| --- | --- | --- |
| Stripe products setup | Create Free/Starter/Pro products in Stripe dashboard | Price IDs exist and match .env |
| Checkout flow | POST /api/billing/checkout → Stripe session → redirect | User can complete checkout and upgrade plan |
| Webhook handler | POST /api/billing/webhook handles 3 events | Plan upgrades + downgrades work end to end |
| UsageBar component | Shows inputs_used/inputs_limit in dashboard | Bar updates after each ingest |
| PlanGate modal | Blocks ingest + shows pricing when over limit | Free users see upgrade prompt, not raw error |

## Sprint 10 — Polish + Error States (Week 11)

| Task | Detail | Done when |
| --- | --- | --- |
| Empty states | All pages have useful empty states (not blank screens) | First-time users are guided to next action |
| Error handling | Transcription fail, Claude fail, Stripe fail — all show friendly messages with retry | No raw error messages visible to user |
| Loading states | Skeletons on all data-fetching pages | No layout shift on load |
| Mobile responsive | All pages usable on mobile | Passes basic mobile viewport test |
| Content history | /dashboard shows all inputs with date, source type, status | User can see full history |

## Sprints 11–12 — Beta (Weeks 12–14)

| Task | Detail | Done when |
| --- | --- | --- |
| Invite 10–15 beta users | Direct outreach to founders in your network | 10+ users have signed up and completed onboarding |
| Fix top 3 bugs | Prioritise blockers from beta feedback | No P0 bugs remaining |
| Voice model QA | Review beta outputs — do they sound personalised? | ≥70% of beta users say outputs sound like them |
| Activation tracking | Log: signup → profile complete → first ingest → first generate | Funnel visible in Supabase dashboard |
| Waitlist page | Simple /waitlist page with email capture for public launch | Waitlist signups flowing before public launch |

# 10. Environment Variables

# Supabase

NEXT_PUBLIC_SUPABASE_URL=

NEXT_PUBLIC_SUPABASE_ANON_KEY=

SUPABASE_SERVICE_ROLE_KEY=      # server-side only — never expose to client

# Anthropic

ANTHROPIC_API_KEY=              # server-side only

# OpenAI (Whisper)

OPENAI_API_KEY=                 # server-side only

# Stripe

STRIPE_SECRET_KEY=              # server-side only

STRIPE_WEBHOOK_SECRET=          # for webhook signature verification

NEXT_PUBLIC_STRIPE_PUBLISHABLE_KEY=

# Stripe price IDs

STRIPE_PRICE_STARTER_MONTHLY=

STRIPE_PRICE_PRO_MONTHLY=

# App

NEXT_PUBLIC_APP_URL=            # e.g. https://foundercopliot.com

# 11. Known Risks & Mitigations — Solo Build

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Loom transcript API unstable | Ingestion fails for Loom URLs | Fall back to file upload; document the limitation clearly in UI |
| Claude response not valid JSON | Generation crashes on parse | Wrap all Claude JSON calls in try/catch; add retry with 'return only valid JSON' reminder |
| Whisper costs spike on large files | Budget overrun | Cap file size at 100MB; show cost warning for files over 30 min |
| Onboarding drop-off before first output | Low activation | Make voice samples optional in onboarding; minimum viable profile = product name + ICP only |
| Streaming breaks on Vercel free tier | Generation timeout | Upgrade to Vercel Pro or use edge runtime; set max_duration = 60s |
| RLS misconfiguration leaks user data | Critical privacy issue | Write RLS policy tests in seed.sql; test with two separate user sessions before beta |

End of document — Founder Copilot Implementation PRD v1.0 — Solo build on Next.js + Supabase + Claude + Whisper + Stripe